## Sprint 1
Feature | Time estimate (days) | Issue # | User stories | Time estimate (days) | Issue # | Who | Dev Tasks | Time estimate (hours) | Architecture Layer
Posting Issue #1 | 18.5d | #7 | Make Public Question Posts | 6d | #44 | T | Create UI screen for post creation | 2h | UI
[5 empty] | #45 | C | Setup a post table schema using C# | 3h | Logic
[5 empty] | #46 | C | Create an endpoint to create a post | 3h | Logic | Timeline:
[5 empty] | #47 | T | Create button to open the screen to create a post | 1h | UI | Sprint 1: due October 9th @ 4:30
[5 empty] | #48 | C | Create post object | 2h | Logic | Sprint 2: due October 30th @ 4:30
[5 empty] | #49 | C | Write unit tests | 4h | Test | Sprint 3: due December 4th @ 4:30
[5 empty] | #50 | C | Write integration tests | 4h | Test
[5 empty] | #51 | C | Write acceptance tests | 4h | Test
|  | #10 | View Public Posts | 6d | #52 | T | Create a screen for viewing public posts | 4h | UI
[5 empty] | #53 | C | Create an endpoint to get public posts | 4h | Logic
[5 empty] | #54 | T | Show information for each post on the screen (i.e. title and first couple sentences of the post) | 2h | UI
[5 empty] | #55 | T | Create tab to navigate to main public posts view (so like a bottom bar) | 1h | UI
[5 empty] | #56 | T | Create a screen for viewing a singular post and comment thread | 2h | UI
[5 empty] | #57 | C | Write unit tests | 4h | Test
[5 empty] | #58 | C | Write integration tests | 4h | Test
[5 empty] | #59 | C | Write acceptance tests | 4h | Test
|  | #9 | See All Public Posts I've Created | 6.5d | #60 | T | Create view to see all posts the user has created | 4h | UI
[5 empty] | #61 | T | Load all public question posts the user has created and replied to in this view | 3h | UI
[5 empty] | #63 | C | Create an endpoint to get all public question posts a user has made | 3h | Logic
[5 empty] | #65 | T | Create a button to open the screen to view all posts a user has made | 1h | UI
[5 empty] | #66 | T | Show information for each post on the screen (same as above user story) | 2h | UI
[5 empty] | #67 | C | Write unit tests | 4h | Test
[5 empty] | #68 | C | Write integration tests | 4h | Test
[5 empty] | #69 | C | Write acceptance tests | 4h | Test
Profile Management Issue #5 | 27d | #20 | Account Creation | 3d | #84 | K | Create UI screen for sign-up | 4h | UI
[5 empty] | #85 | K | Create an endpoint to add new Yapper to user pool | 4h | Logic
[5 empty] | #83 | Q | Write acceptance tests | 4h | Test
|  | #21 | Account Login | 2.5d | #86 | K | Create UI screen for sign-in | 4h | UI
[5 empty] | #87 | K | Connect AWS authenticator for sign-in validation | 2h | Logic
[5 empty] | #78 | Q | Write acceptance tests | 4h | Test
|  | #22 | Edit Account Details | 9.5d | #38 | Q | Create an endpoint to allow user to update their information | 4h | Logic
[5 empty] | #73 | Q | Write unit tests | 4h | Test
[5 empty] | #74 | Q | Write integration tests | 4h | Test
[5 empty] | #75 | Q | Write acceptance tests | 4h | Test
[5 empty] | #88 | K | Connect to AWS Cognito for password reset | 2h | Logic
[5 empty] | #89 | K | Create UI screen for profile dashboard | 4h | UI
[5 empty] | #112 | K | Create UI component for the profile dashboard's list of posts | 4h | UI
[5 empty] | #113 | K | Create UI component for the profile dashboard's list of friends | 4h | UI
[5 empty] | #114 | K | Create UI component for the profile dashboard's list of achievements | 4h | UI
[5 empty] | #115 | K | Create component for changing password in profile dashboard | 4h | UI
|  | #23 | Make Friends | 12d | #39 | Q | Create an endpoint to get all friends | 4h | Logic
[5 empty] | #40 | Q | Setup a friend table schema using c# | 4h | Logic
[5 empty] | #41 | Q | Create an endpoint to send a friend request | 4h | Logic
[5 empty] | #42 | Q | Create an endpoint to accept/decline a friend request | 4h | Logic
[5 empty] | #43 | Q | Create an endpoint to list all friend requests | 4h | Logic
[5 empty] | #70 | Q | Write unit tests | 4h | Test
[5 empty] | #71 | Q | Write integration tests | 4h | Test
[5 empty] | #72 | Q | Write acceptance tests | 4h | Test
[5 empty] | #90 | K | Create UI screen to send friend request | 4h | UI
[5 empty] | #113 | K | Create UI component for the profile dashboard's list of friends | 4h | UI
[5 empty] | #116 | K | Create UI screen to view all pending requests | 4h | UI
[5 empty] | #117 | K | Create UI component to accept/decline a friend request | 4h | UI
Notifications Issue #24 |  | #26 | Diary Entry Notifications
|  | #27 | New Achievement Notifications
|  | #28 | Friend Request Notifications
|  | #29 | Daily yAPP Notifications
Post Tags Issue #25 |  | #30 | Add Tags to Posts
|  | #31 | Search Tags
|  | #32 | Filter Tags
[5 empty] | #117 | K | Create UI component to accept/decline a friend request | 4h | UI
[5 empty] | #116 |  | Create UI component to view all pending requests

## Sprint 2
Feature | Time estimate (days) | Issue # | User stories | Time estimate (days) | Issue # | Who | Dev Tasks | Time estimate (hours) | Architecture Layer
Interactions with Posts Issue #2 | 15.5d | #13 | Reply to Public Posts | 9d | #193 | T | Create an endpoint to get all comments that have the same parent post | 3h | Logic
[5 empty] | #64 | T | Create an endpoint to get all comments a user has posted | 3h | Logic
[5 empty] | #194 | T | Create an endpoint to make a new comment | 3h | Logic
[5 empty] | #62 #195 | Q | Link to original public question posts for all replies the user has made when viewing a comment on the screen for viewing all posts a user has made | 2h + 3h | UI
[5 empty] | #196 #197 | Q | Create a screen to write a comment on a public post | 3h + 4h | UI
[5 empty] | #198 | T | Create a comment table in dynamoDB | 3h | Logic
[5 empty] | #199 | T | Create a comment model/schema | 3h | Logic
[5 empty] | #200 #201 | Q | Display comments on each public post when a post is opened | 3h + 4h | UI
[5 empty] | #202 | T | Unit tests | 4h | Test
[5 empty] | #203 | T | Integration tests | 4h | Test
[5 empty] | #204 | Q | Acceptance tests | 3h | Test
|  | #153 | Edit/Delete Posts and Comments | 6.5d | #205 | T | Create endpoint to delete a comment | 3h | Logic
[5 empty] | #206 | T | Create an endpoint to edit a comment | 2h | Logic
[5 empty] | #207 #208 | Q | Add a button to a post to edit the post, which will open the editing screen to update the post | 3h + 4h | UI
[5 empty] | #209 #210 | Q | Add a button to a post to delete the post | 1h + 2h | UI
[5 empty] | #211 #212 | Q | Add a button to a comment to edit the comment, which will open the editing screen to update the comment | 1.5h + 2.5h | UI
[5 empty] | #213 #214 | Q | Add a button to a comment to delete the comment | 1h + 2h | UI
[5 empty] | #215 | T | Unit tests | 4h | Test
[5 empty] | #216 | T | Integration tests | 4h | Test
[5 empty] | #217 | Q | Acceptance tests | 2h | Test
Personal Calendar Issue #3 | 12d | #8 | Make Diary Entry Posts | 2d | #154 #155 | C | Create toggle on post creation screen to change public question to a diary entry post | 1h + 2h | UI
[5 empty] | #156 #157 | C | Create toggle on post creation when the post is a diary entry to choose whether to post diary entry as anonymous or not | 1h + 2h | UI
[5 empty] | #158 | C | Acceptance tests | 3h | Test
|  | #14 | View My Diary Entries on My Calendar | 6d | #159 | K | Create endpoint to get diary entries by date and username | 2h | Logic
[5 empty] | #160 #161 | C | Create UI calendar component | 4h + 5h | UI
[5 empty] | #162 #163 | C | Create view under calendar that displays diary entries from day that is selected, where brief information on each diary entry is displayed | 4h + 5h | UI
[5 empty] | #164 | K | Unit tests | 2h | Test
[5 empty] | #165 | K | Integration tests | 2h | Test
[5 empty] | #166 | C | Acceptance tests | 3h | Test
[5 empty] | #167 #168 | C | View full diary entry when the diary entry is clicked on the calendar view | 1h + 2h | UI
|  | #15 | View My Friend's Diary Entries on My Calendar | 4d | #169 | K | Create endpoint to get all diary entries from all friends | 3h | Logic
[5 empty] | #170 #171 | C | Create screen for viewing an individual diary entry | 2h + 3h | UI
[5 empty] | #172 #173 | C | Display brief information on each diary entry from friends on calendar view on the day the entry was created | 2h + 3h | UI
[5 empty] | #174 | K | Unit tests | 2h | Test
[5 empty] | #175 | K | Integration tests | 2h | Test
[5 empty] | #176 | C | Acceptance tests | 3h | Test

## Sprint 3
Feature | Time estimate (days) | Issue # | User stories | Time estimate (days) | Issue # | Who | Dev Tasks | Time estimate (hours) | Architecture Layer
Hidden Achievement System Issue #4 | 6d | #16 | See Earned Achievements | 1.5d | #289 #290 | K | Create cards to display achievements on | 2h + 2h | UI
[5 empty] | #291 #292 | K | Load all achievements onto the "My Awards" view | 1h + 1h | UI
[5 empty] | #293 | C | Acceptance tests | 0.5h | Test
[5 empty] | stretch |  | Attach achievements to the post they were achieved on in viewing a post full-screen |  | UI
[5 empty] | stretch |  | Create a view to see an achievement full-screen |  | UI
[5 empty] | stretch |  | Create a link on the card to see which post the user got an achievement on |  | UI
|  | #17 | Earn Achievements | 4.5d | #294 | C | Create an endpoint to get all achievements from a user | 2h | Logic
[5 empty] | #295 | C | Create an endpoint to create an achievement | 2h | Logic
[5 empty] | #296 | C | Trigger achievement creation in backend when post is loaded somewhere? Or periodically check for achievements? | 3h? | Logic
[5 empty] | #297 | C | Create an endpoint to get a single achievement based on an id | 2h | Logic
[5 empty] | #298 | C | Create an achievement table in the database | 0.5h | Logic
[5 empty] | #299 | C | Create an achievement model/schema | 0.5h | Logic
[5 empty] | #300 | C | Delete all achievements associated with a post when that post is deleted | 2h | Logic
[5 empty] | #301 | C | Unit tests | 2h | Test
[5 empty] | #302 | C | Integration tests | 2h | Test
[5 empty] | #303 | C | Create a dictionary of all possible achievements + actions to manage those achievements | 2h | Logic
[5 empty] | #304 | C | Create an endpoint to get all achievements based on a post id | 2h | Logic
Interactions with Posts Issue #2 | 9d | #11 | Upvote Public Posts | 5d | #177 | T | Create an endpoint to upvote a post | 3h | Logic
[5 empty] | #178 | T | Create an endpoint to upvote a comment | 3h | Logic
[5 empty] | #179 | T | Create an endpoint to remove an upvote from a post | 3h | Logic
[5 empty] | #180 #181 | Q | Add an upvote button to each post and comment | 1h + 2h | UI
[5 empty] | #182 | T | Unit tests | 4h | Test
[5 empty] | #183 | T | Integration tests | 4h | Test
[5 empty] | #184 | Q | Acceptance tests | 2h | Test
[5 empty] | #249 | T | Create an endpoint to remove an upvote from a comment | 3h | Logic
[5 empty] | #311 | T | Create upvote/downvote table in the database | 1h | Logic
[5 empty] | #312 | T | Create an upvote/downvote model/schema | 1h | Logic
|  | #12 | Downvote Public Posts | 4d | #185 | T | Create an endpoint to downvote a post | 2h | Logic
[5 empty] | #186 | T | Create an endpoint to downvote a comment | 2h | Logic
[5 empty] | #187 | T | Create an endpoint to remove a downvote from a post | 2h | Logic
[5 empty] | #188 #189 | Q | Add a downvote button to each post and comment | 1h + 2h | UI
[5 empty] | #190 | T | Unit tests | 4h | Test
[5 empty] | #191 | T | Integration tests | 4h | Test
[5 empty] | #192 | Q | Acceptance tests | 2h | Test
[5 empty] | #250 | T | Create an endpoint to remove a downvote from a comment | 2h | Logic
Notifications Issue #24 |  | #26 | Diary Entry Notifications
|  | #27 | New Achievement Notifications
|  | #28 | Friend Request Notifications
|  | #29 | Daily yAPP Notifications
Post Tags Issue #25 |  | #30 | Add Tags to Posts
|  | #31 | Search Tags
|  | #32 | Filter Tags